# Executive Summary

## AP-05 Executive Summary - 91.200(c), 91.220(b)

1.	Introduction

In 2006, the United States Department of Housing and Urban Development (HUD) identified the Village of Hoffman Estates as a Community Development Block Grant (CDBG) entitlement community. The Annual Action Plan (AAP) is a one-year plan that provides a detailed description of resources to be used and projects to be undertaken by the Village in effort to address the priority needs and specific objectives that were identified within the Village’s 2025-2029 CDBG Consolidated Plan.
In 2014, the Village joined the Cook County’s HOME Consortium. As a result of this coordination between the Village, Cook County, and other HOME Consortium communities, the Village’s Consolidated Plan for Program Years 2025-2029 is part of the larger Cook County Consolidated Plan for those years. This current Annual Action Plan (AAP) is based on the goals set forth in that Consolidated Plan. Although the Village participates in the HOME Consortium, it still receives a direct allocation of CDBG funding from HUD each year in order to address projects within the Village of Hoffman Estates.
This Annual Action Plan lists the activities to be carried out using CDBG funds during Program Year (PY) 2026, which runs from October 1, 2026, through September 30, 2027. PY 2026 marks over twenty years that the Village has participated in the CDBG program, and the second year of the Village’s current 5-year Consolidated Plan. The Village anticipates an allocation of $238,046 in grant money for the upcoming year, a small increase from the prior PY. The Village proposes to use the CDBG funds for 
• public facility infrastructure projects (specifically three (3) nonprofit facility improvement projects)
• administration of the CDBG program, 
• a public infrastructure project coordinated as part of the Village’s 2027 Street Revitalization program

2.	Summarize the objectives and outcomes identified in the Plan

This could be a restatement of items or a table listed elsewhere in the plan or a reference to another location. It may also contain any essential items from the housing and homeless needs assessment, the housing market analysis or the strategic plan.

Based on the needs assessment and market analysis, as well as consideration of the limited anticipated resources, the Village developed a strategic plan to use CDBG funds to meet its priority housing, homeless, and community development needs. The Village of Hoffman Estates identified two primary objectives for the 2025-2029 Consolidated Plan, which carry through to the PY 2026 Annual Action Plan. Within these objectives are individual goals, projects, and performance measures to ensure progress towards addressing priority needs. These objectives are described in greater detail in the Strategic Plan.
Objective 1: Provide improvements to public infrastructure and public facilities in order to create a suitable living environment, which will promote or provide for improved accessibility, safety, and sustainability in existing neighborhoods. The Village proposes to assist public facility and public infrastructure projects within eligible CDBG neighborhoods or utilized primarily by low-moderate income individuals and families.
Objective 2: Provide decent housing through access to affordable housing services and programs, including housing maintenance and rehabilitation services to limited-income individuals and households, in order to maintain affordability and accessibility in home ownership.

3.	Evaluation of past performance

This is an evaluation of past performance that helped lead the grantee to choose its goals or projects.

During the many years Hoffman Estates has operated CDBG, the Village has diligently invested over $4 million in CDBG funds, all in accordance with HUD policies and procedures towards the two key objectives.
During the current year, PY 2025, $183,662 of CDBG funding is expected to be utilized for street rehabilitation. Through years of economic distress, the Village has relied on CDBG funds to address such infrastructure projects in a timely fashion.
The Village continues to partner with the North West Housing Partnership (NWHP) for the administration of the Single Family Rehabilitation (SFR) program. The program provides a zero-interest deferrable loan (now forgivable if the loan is held long enough) to low- income residents who hold equity in their home. The goal of this rehabilitation activity has been to allow recipients to maintain their own homes, improve their individual environments, and contribute to the overall sustainability of affordable neighborhoods. While the COVID- 19 pandemic slowed activity in the program during 2020-2022, more recently interest has grown, in part thanks to increasing funding and making the loan forgivable if held long enough. 
The Village has previously utilized CDBG funding for needed infrastructure repairs at the Children’s Advocacy Center (CAC), which is located in a Village-owned building. Substantial work has been completed at the facility over the past ten years utilizing pooled CDBG funding from neighboring communities as well. During Program Years 2019 - 2021, projects at the CAC did not take place due to the ongoing pandemic. During 2020, the CAC did apply for and was granted funding for PPE through the Village’s CDBG-CV program, for pandemic relief. During 2022-2025 physical work was not performed at the CAC site due to a neighboring Leaking Underground Storage Tank (LUST) issue remaining, preventing an environmental review from being able to clear the site contamination section – Hoffman Estates’ Public Works has earned a NFR letter to clear said issue, with hopes that physical work at CAC can restart in 2026-2027, as CAC finishes up work on a state grant project and CAC still has work required for their facility.

Working with Cleabrook on CDBG-CV in the past has led to an ongoing relationship with interest in standard CDBG funding as well.

4.	Summary of Citizen Participation Process and consultation process

Summary from citizen participation section of plan.

The Village’s public hearing regarding the development of the PY 2026 Annual Action Plan will take place on July 22, 2026, at Village Hall. The hearing is held annually to obtain comments on the Draft Annual Action Plan as well as to obtain feedback on community needs and how they might be addressed through the CDBG funding.
The PY 2026 Draft Annual Action Plan will be available for a 30-day public review and comment from June 27th, 2026, to August 3, 2026, and open for discussion at the Planning, Building and Zoning (PBZ) Committee public meeting on August 3, 2026. The public comment period, public hearing, and public meeting were noticed on the Village Website (www.hoffmanestates.org/cdbg ) and in the Daily Herald, the local newspaper. The Draft Plan document was available for public viewing at Village Hall and on the Village website during the entire public comment period. The Village also made the Draft Plan known to local organizations and stakeholders through the means of a traditional mailing to approximately 120 interested recipients, mailed out on June 23, 2026.

5.	Summary of public comments

This could be a brief narrative summary or reference an attached document from the Citizen Participation section of the Con Plan.

Currently none - this section will be updated as they are recorded

6.	Summary of comments or views not accepted and the reasons for not accepting them

Currently none - this section will be updated as they are recorded

7.	Summary

Hoffman Estates, through Development Services, seeks to address the needs of the residents and community-focused organizations throughout the Village based on analysis of the needs assessment and market analysis, as well as consideration of the limited anticipated resources. The Village developed a strategic plan to use CDBG funds to meet its priority housing, and related developmental needs while staying within compliance of HUD regulations based upon input from relevant stakeholders. Development Services acquired public input per our Citizen Participation Plan as required. Hoffman Estates will continue to make the necessary adjustments to create the most impactful project, which is why we have added a new program this year in order to best address the needs of our community.

## PR-05 Lead & Responsible Agencies - 91.200(b)

1.	Agency/entity responsible for preparing/administering the Consolidated Plan

The following are the agencies/entities responsible for preparing the Consolidated Plan and those responsible for administration of each grant program and funding source.

| Agency Role | Name | Department/Agency |
| --- | --- | --- |

| CDBG Administrator | HOFFMAN ESTATES | Development Services |
| --- | --- | --- |

Table 1 – Responsible Agencies

Narrative

Since becoming an entitlement community in 2006, individuals in the Hoffman Estates Development Services Department have administered the CDBG program. The department consists of four divisions that coordinate all aspects of residential and commercial development as well as manage significant infrastructure improvements in Hoffman Estates. The department works with residents and existing businesses on property improvements, and with the development community to bring new businesses to Hoffman Estates. The department provides information and professional services to residents, developers, realtors, contractors, governmental agencies, and other interested parties on a variety of topics.
The divisions within the Development Services department which perform services related to HUD priorities include the Planning & Transportation Division, the Engineering Division, the Code Enforcement Division, and the Economic Development Division. The Village’s Health and Human Services (HHS) Department located at Village Hall as well as the Village’s Police Department perform many of the responsibilities related to social services. The Finance Department provides administrative support. The Village of Hoffman Estates as a collective will work towards accomplishing this Annual Action Plan.

Consolidated Plan Public Contact Information

Village of Hoffman Estates
Michael Walker – Community Planner II
(michael.walker@vohe.org)
1900 Hassell Road
 Hoffman Estates, IL 60169
 Phone: 847-781-2669
https://www.hoffmanestates.org/services/housing_support___cdbg.php

## AP-10 Consultation - 91.100, 91.200(b), 91.215(l)

1.	Introduction

The Village consulted with a number of local social service agencies that serve Hoffman Estates in order to identify and prioritize needs to include in the current Consolidated Plan. These included health services agencies, social services related to children, agencies that serve the homeless, neighboring municipalities, the park district, and the Cook County Community Development Department. The Village is a member of the Cook County HOME Consortium. The Village also has a Health & Human Services (HHS) department that, in addition to providing low-cost vaccination clinics and mental health services, also works with area non-profit and governmental agencies to coordinate services for citizens in need.
The Village maintains a list of over 100 public, private, and nonprofit stakeholder organizations and individuals that fit into these and other categories. A copy of this list is included as an attachment to the Plan. These organizations are critical to informing policy decisions regarding decent housing, suitable living environments, and expanded economic opportunity. These individuals were invited to consult individually with the Village and to provide input through the general citizen participation process. 
They receive mailings on all annual CDBG planning functions.
Several agencies from this list were individually consulted in order to ensure their challenges and needs were considered in the development of this Plan.

Provide a concise summary of the jurisdiction’s activities to enhance coordination between public and assisted housing providers and private and governmental health, mental health and service agencies (91.215(l)).

Membership in the Cook County HOME Consortium positions the Village to be part of the regional discussion with public and assisted housing providers as well as other municipalities to help coordinate services.
The Village's Health and Human Services Department (HHS) provides professional and affordable physical and mental health services to residents in the Village of Hoffman Estates. It serves as the primary point of contact for coordination with other private health, mental health, and social service agencies. Among the services they provide are immunizations, health screenings, TB testing, and individual/family counseling. The Department's capacity is limited, and therefore coordination with other providers is crucial. In situations in which HHS is not able to directly provide services for foreclosure counseling, medical needs, financial assistance, food pantry, and youth services, the Department will refer clients to appropriate care providers.

Describe coordination with the Continuum of Care and efforts to address the needs of homeless persons (particularly chronically homeless individuals and families, families with children, veterans, and unaccompanied youth) and persons at risk of homelessness.

The Village will coordinate with the local Continuum of Care to assess the urgency of addressing homelessness in the Village of Hoffman Estates. While the Village is not required to compile and submit a full homeless needs assessment due to its membership in the HOME Consortium, staff will continue to reach out social service agencies to understand the extent of homelessness in the Village and coordinate assistance.

Describe consultation with the Continuum(s) of Care that serves the jurisdiction’s area in determining how to allocate ESG funds, develop performance standards for and evaluate outcomes of projects and activities assisted by ESG funds, and develop funding, policies and procedures for the operation and administration of HMIS

Although the Village does not receive ESG funds, as discussed in the previous answer, the Village will consult individually with the Continuum of Care to assess homelessness in the Village and determine how to address it in the Consolidated Plan.

2.	Agencies, groups, organizations and others who participated in the process and consultations

Table 2 – Agencies, groups, organizations who participated

| 1 | Agency/Group/Organization | HOFFMAN ESTATES |
| --- | --- | --- |
|  | Agency/Group/Organization Type | Health Agency Agency - Emergency Management Other government - Local |
|  | What section of the Plan was addressed by Consultation? | Housing Need Assessment Public Housing Needs Homeless Needs - Chronically homeless Homeless Needs - Families with children Homelessness Needs - Veterans Homelessness Needs - Unaccompanied youth Homelessness Strategy Non-Homeless Special Needs Market Analysis Anti-poverty Strategy Lead-based Paint Strategy |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | The Health & Human Services (HHS) Department has a number of needs related to social work, immunizations, counseling, homelessness prevention and homelessness needs. The Village's Emergency Management Agency maintains a disaster response plan, a weather alert system, warming/cooling centers, and provides a variety of other support efforts, as well as being a member of the Joint Emergency Management System with a group of 10 area municipalities. |
| 2 | Agency/Group/Organization | CHILDREN'S ADVOCACY CENTER OF NORTH AND NORTHWEST COOK COUNTY |
|  | Agency/Group/Organization Type | Services-Children Services-Victims of Domestic Violence Services-Education Services - Victims Child Welfare Agency |
|  | What section of the Plan was addressed by Consultation? | Homeless Needs - Families with children Non-Homeless Special Needs Market Analysis |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | The CAC coordinates services for children who are victims of sexual or physical abuse in partnership with local law enforcement agencies and the Illinois Department of Children and Family Services (DCFS). All cases of such type in the northern and northwestern Cook County suburbs pass through the CAC in Hoffman Estates or its satellite location. The Village of Hoffman Estates leases and maintains an old Village Hall. |
| 3 | Agency/Group/Organization | NORTH WEST HOUSING PARTNERSHIP |
|  | Agency/Group/Organization Type | Housing Services - Housing |
|  | What section of the Plan was addressed by Consultation? | Housing Need Assessment Public Housing Needs Market Analysis Lead-based Paint Strategy |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | NWHP has been a subrecipient of CDBG funds from the Village for more than 15 years. The agency provides a number of programs for low to moderate income residents in the northwest suburbs. The Village continued to seek their input on this Consolidated Plan and will continue to fund the single family rehabilitation program using CDBG funds when additional funds are necessary. The agency expressed a desire to continue administering the single family rehab (SFR) program for the Village. |
| 4 | Agency/Group/Organization | Cook County Department of Planning and Development |
|  | Agency/Group/Organization Type | Housing Services - Housing Other government - County |
|  | What section of the Plan was addressed by Consultation? | Housing Need Assessment Public Housing Needs Homeless Needs - Chronically homeless Homeless Needs - Families with children Homelessness Needs - Veterans Homelessness Needs - Unaccompanied youth Homelessness Strategy Non-Homeless Special Needs Market Analysis Economic Development Anti-poverty Strategy Lead-based Paint Strategy |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | The Village coordinates to share information as it relates to our respective Consolidated Plans. Cook County is the Lead Organization of the Cook County HOME Consortium and HOME funding information is also reviewed. The Village will consider portions of the AFH that may be applicable to the Village. |
| 5 | Agency/Group/Organization | SCHAUMBURG |
|  | Agency/Group/Organization Type | Other government - Local |
|  | What section of the Plan was addressed by Consultation? | Housing Need Assessment Public Housing Needs Homeless Needs - Chronically homeless Homeless Needs - Families with children Homelessness Needs - Veterans Homelessness Needs - Unaccompanied youth Homelessness Strategy Non-Homeless Special Needs Market Analysis Economic Development Anti-poverty Strategy Lead-based Paint Strategy |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | The Village of Schaumburg shares a significant boundary with the Village of Hoffman Estates. They are also a CDBG entitlement community and member of the Cook County HOME Consortium. The Village consulted in order to identify areas for potential collaboration around CDBG programs and services. Since Hoffman Estates residents often work, shop, and socialize in Schaumburg and vice versa, opportunities for coordination, joint marketing, and promotion were discussed. |
| 6 | Agency/Group/Organization | PALATINE |
|  | Agency/Group/Organization Type | Other government - Local |
|  | What section of the Plan was addressed by Consultation? | Housing Need Assessment Public Housing Needs Homeless Needs - Chronically homeless Homeless Needs - Families with children Homelessness Needs - Veterans Homelessness Needs - Unaccompanied youth Homelessness Strategy Non-Homeless Special Needs Market Analysis Economic Development Anti-poverty Strategy Lead-based Paint Strategy |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | The Village of Palatine is a neighboring municipality to the Village of Hoffman Estates, a CDBG entitlement community, and member of the Cook County HOME Consortium. The Village consulted in order to identify areas for potential collaboration around CDBG programs and services |
| 7 | Agency/Group/Organization | MOUNT PROSPECT |
|  | Agency/Group/Organization Type | Other government - Local |
|  | What section of the Plan was addressed by Consultation? | Housing Need Assessment Public Housing Needs Homeless Needs - Chronically homeless Homeless Needs - Families with children Homelessness Needs - Veterans Homelessness Needs - Unaccompanied youth Homelessness Strategy Non-Homeless Special Needs Market Analysis Economic Development Anti-poverty Strategy Lead-based Paint Strategy |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | Mt. Prospect was consulted as a fellow HOME Consortium member and nearby municipality. Continued coordination between Mount Prospect and Hoffman Estates is anticipated as a result of joint membership in the consortium. |
| 8 | Agency/Group/Organization | DES PLAINES |
|  | Agency/Group/Organization Type | Other government - Local |
|  | What section of the Plan was addressed by Consultation? | Housing Need Assessment Public Housing Needs Homeless Needs - Chronically homeless Homeless Needs - Families with children Homelessness Needs - Veterans Homelessness Needs - Unaccompanied youth Homelessness Strategy Non-Homeless Special Needs Market Analysis Economic Development Anti-poverty Strategy Lead-based Paint Strategy |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | Des Plaines was consulted as a fellow HOME Consortium member and nearby municipality. Continued coordination is anticipated as a result of joint membership in the consortium. |
| 9 | Agency/Group/Organization | ARLINGTON HEIGHTS |
|  | Agency/Group/Organization Type | Other government - Local |
|  | What section of the Plan was addressed by Consultation? | Housing Need Assessment Public Housing Needs Homeless Needs - Chronically homeless Homeless Needs - Families with children Homelessness Needs - Veterans Homelessness Needs - Unaccompanied youth Homelessness Strategy Non-Homeless Special Needs Market Analysis Economic Development Anti-poverty Strategy Lead-based Paint Strategy |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | Arlington Heights was consulted as a fellow HOME Consortium member and nearby municipality. Continued coordination between Arlington Heights and Hoffman Estates is anticipated as a result of joint membership in the consortium. |
| 10 | Agency/Group/Organization | SKOKIE |
|  | Agency/Group/Organization Type | Other government - Local |
|  | What section of the Plan was addressed by Consultation? | Housing Need Assessment Public Housing Needs Homeless Needs - Chronically homeless Homeless Needs - Families with children Homelessness Needs - Veterans Homelessness Needs - Unaccompanied youth Homelessness Strategy Non-Homeless Special Needs Market Analysis Economic Development Anti-poverty Strategy Lead-based Paint Strategy |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | Skokie has been very helpful at HOME Consortium meetings and Hoffman Estates is looking forward to continued coordination, which is anticipated as a result of Skokie joining the Consortium for us to have a joint membership in the consortium. |
| 11 | Agency/Group/Organization | CLEARBROOK |
|  | Agency/Group/Organization Type | Housing Services - Housing Services-Persons with Disabilities Services-Education |
|  | What section of the Plan was addressed by Consultation? | Non-Homeless Special Needs |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | Hoffman Estates has met with Clearbrook to discuss the upcoming needed work on their various properties. Both in this Action Plan and future Action Plans, Hoffman Estates expects to have CDBG projects to address the physical work on several of their properties within Hoffman Estates. |
| 12 | Agency/Group/Organization | Leyden Family Service |
|  | Agency/Group/Organization Type | Services-Health Health Agency |
|  | What section of the Plan was addressed by Consultation? | alcohol and drug abuse detoxification and rehabilitation treatment |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | Hoffman Estates has been coordinating with Leyden Family Service's SHARE Program to work on assisting with CDBG funds to allow them to operate not-for-profit residential alcohol and drug abuse detoxification and rehabilitation treatment facility within Hoffman Estates. |
| 13 | Agency/Group/Organization | Access to Care |
|  | Agency/Group/Organization Type | Services-Health Health Agency |
|  | What section of the Plan was addressed by Consultation? | Health - assistance for uninsured & underinsured |
|  | Briefly describe how the Agency/Group/Organization was consulted. What are the anticipated outcomes of the consultation or areas for improved coordination? | Access to Care is interested in funding for the clients who are residents of Hoffman Estates, though they have no physical presence in Hoffman Estates. While Hoffman Estates' CDBG focus remains on physical construction, effort is being put into assisting with other funds. |

Identify any Agency Types not consulted and provide rationale for not consulting

N/A

Other local/regional/state/federal planning efforts considered when preparing the Plan

| Name of Plan | Lead Organization | How do the goals of your Strategic Plan overlap with the goals of each plan? |
| --- | --- | --- |
| Continuum of Care | Cook County | As the lead agency for the Cook County HOME Consortium, Cook County coordinates the Continuum of Care for the region including Hoffman Estates. CoC also provides coordination on fair housing compliance. |
| Comprehensive, Transportation, Development Code | Village of Hoffman Estates | The Village has completed two Area Plans and is updating its Comprehensive Plan, Development Codes and a new Multi-Modal Transportation Plan. Affordable, decent housing and access to various forms of affordable transportation are a priority of the plans. Data from the Consolidated Plan is used to inform decisions and policies in these efforts. |
| Planning for Progress | Cook County | As the lead agency for the Cook County HOME Consortium, Cook County's Department of Planning and Development created Planning for Progress which outlined four key priority objectives, all of which are also important to the Village of Hoffman Estates. Among these goals were infrastructure and housing, both of which the Village intends to address through CDBG funds. |
| ON TO 2050 | CMAP | Being spread across several government jurisdictions and sharing borders with 8 other municipalities means Hoffman Estates must be viewed in a regional context. CMAP's ON TO 2050 regional vision contains recommendation areas. All of these themes relate to Hoffman Estates to varying degrees, but all have at least some importance. |
| Analysis of Impediments (AI) | Village of Hoffman Estates | The Village's AI assesses the level of fair housing choice within the Village's jurisdiction, identifies potential impediments to fair housing choice, and recommends actions that the Village and partners can take to eliminate or remedy improvements. The Village continues to make progress towards action items identified in the AI. The Assessment of Fair Housing (AFH) process, which would have replaced AI, was terminated by HUD in late 2020. |
| Flexible Transit Service | Village of Hoffman Estates | The Village published a flexible transit service operations plan through the Regional Transit Authority which included consultation with various transit service providers. The plan identifies other transit needs and areas for coordination. |

Table 3 - Other local / regional / federal planning efforts

Narrative

The Village works with internet service provides and the public library district to ensure the community continues to close the digital divide and ensure residents have internet access in one form or another.

## AP-12 Participation - 91.401, 91.105, 91.200(c)

1.	Summary of citizen participation process/Efforts made to broaden citizen participation

Summarize citizen participation process and how it impacted goal-setting

The citizen participation process included a traditional mailing to interested parties (individuals, non-profit and other local organizations), a newspaper notice, a 30-day public comment period, draft plan posted on the Village website, a public hearing, and two public meetings.

Citizen Participation Outreach

| Sort Order | Mode of Outreach | Target of Outreach | Summary of response/attendance | Summary of comments received | Summary of comments not accepted and reasons | URL (If applicable) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Public Hearing | Minorities Persons with disabilities Non-targeted/broad community Residents of Public and Assisted Housing | Public Hearing will be held at Village Hall on July 22, 2026 | No comments have yet been received | N/A | N/A |
| 2 | Public Meeting | Minorities Persons with disabilities Non-targeted/broad community Residents of Public and Assisted Housing | Planning, Building and Zoning (PBZ) Meeting August 3, 2026 | No comments have yet been received | No comments have yet been received | N/A |
| 4 | Newspaper Ad | Minorities Persons with disabilities Non-targeted/broad community Residents of Public and Assisted Housing | Newspaper comment period in the Daily Herald Public Notice began on the June 26, 2026. No comments have been received. | No comments have yet been received | No comments have yet been received | N/A |
| 5 | Internet Outreach | Minorities Persons with disabilities Non-targeted/broad community Residents of Public and Assisted Housing | Notice of Draft Plan on Village's CDBG Webpage and Plan available for view on June 25, 2026. | No comments have yet been received | No comments have yet been received | https://www.hoffmanestates.org/services/housing_support___cdbg.php |

Table 4 – Citizen Participation Outreach

# Expected Resources

## AP-15 Expected Resources - 91.420(b), 91.220(c)(1,2)

Introduction

These are the funds that are expected to be programmed.

Anticipated Resources

| Program | Source of Funds | Uses of Funds | Expected Amount Available Year 1 |  |  |  | Expected Amount Available Remainder of ConPlan $ | Narrative Description |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Annual Allocation: $ | Program Income: $ | Prior Year Resources: $ | Total: $ |  |  |
| CDBG | public - federal | Acquisition Admin and Planning Economic Development Housing Public Improvements Public Services | 238,046.00 | 23,010.00 | 70,440.00 | 331,496.00 | 750,000.00 | Entering year two of five from the ConPlan. |

Table 1 - Expected Resources – Priority Table

Explain how federal funds will leverage those additional resources (private, state and local funds), including a description of how matching requirements will be satisfied

Village encourages leveraging, but does not require it.

If appropriate, describe publically owned land or property located within the jurisdiction that may be used to address the needs identified in the plan

CAC operates within a leased building owned by Hoffman Estates in order to assist their clients.

Discussion

Expecting program income (PI) in the amount of $23,010, unexpended from cancelled projects/program income.

# Annual Goals and Objectives

AP-20 Annual Goals and Objectives - 91.420, 91.220(c)(3)&(e)

Goals Summary Information

| Sort Order | Goal Name | Start Year | End Year | Category | Geographic Area | Needs Addressed | Funding | Goal Outcome Indicator |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Planning and Administration | 2025 | 2029 | Planning and Administration | Village Wide | Improving Public Facilities and Infrastructure Non-Housing Economic Development Needs Reducing the Housing Cost Burden Social Service Needs- Homelessness Social Service Needs- Other | CDBG: $47,600.00 | Other: 1 Other |
| 2 | Public Facilities Improvements | 2025 | 2029 | Non-Housing Community Development |  | Social Service Needs- Other | CDBG: $152,000.00 | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit: 200 Persons Assisted |
| 3 | Public Infrastructure Improvements | 2025 | 2029 | Non-Housing Community Development | Village Wide | Improving Public Facilities and Infrastructure | CDBG: $131,896.00 | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit: 200 Persons Assisted |

Table 2 – Goals Summary

Goal Descriptions

| 1 | Goal Name | Planning and Administration |
| --- | --- | --- |
|  | Goal Description | CDBG administration funds |
| 2 | Goal Name | Public Facilities Improvements |
|  | Goal Description | CAC projects continue to ensure property is able to meet the needs of the organization and its clients - funded at $25,000. Clearbrook will have two (2) projects, one funded at $12,000 and another at $15,000 = $27,000 in total. SHARE Leyden will also have a project at $100,000. Collectively, they are funded at $152,000. |
| 3 | Goal Name | Public Infrastructure Improvements |
|  | Goal Description | 2026-2027 CDBG funding will continue to positively impact the physical infrastructure of the Village - mostly roadways and sidewalks - as needed and determined by the Village's Engineering team. |

## AP-35 Projects - 91.420, 91.220(d)

Introduction

During the 2026-2027 program year, the Village proposes using funds for public infrastructure, numerous nonprofit & public facilities, and planning and administration.

| # | Project Name |
| --- | --- |
| 1 | Planning and Administration |
| 2 | Public Facilities Improvement - Children's Advocacy Center (CAC) Rehabilitation |
| 3 | Street & Related Improvements |
| 4 | Clearbrook 1 - Bathroom |
| 5 | Clearbrook 2 - Shade |
| 6 | The SHARE Program Facility Improvements |

Table 3 – Project Information

Describe the reasons for allocation priorities and any obstacles to addressing underserved needs

Hoffman Estates aims to allocate funds to meet municipal and non-profit agency needs, within the constraints of diminishing resources and various regulations. With a decreasing number of eligible census tracts/block groups for neighborhood investment/municipal infrastructure, allocation priorities are shifting to other unmet needs in the community. A major obstacle to meeting these underserved needs is the inability to plan out the reallocation of program income, as property selloffs could occur at any point, which prevents ideal long-range planning - and going forward, loans will eventually be forgiven.  Development Services will continue to weigh community input in creating the allocation priorities for future funding.

## AP-38 Project Summary

Project Summary Information

| 1 | Project Name | Planning and Administration |
| --- | --- | --- |
|  | Target Area |  |
|  | Goals Supported | Planning and Administration |
|  | Needs Addressed | Improving Public Facilities and Infrastructure Reducing the Housing Cost Burden Social Service Needs- Homelessness Non-Housing Economic Development Needs Social Service Needs- Other |
|  | Funding | CDBG: $47,600.00 |
|  | Description | CDBG administration |
|  | Target Date | 9/30/2027 |
|  | Estimate the number and type of families that will benefit from the proposed activities | N/A |
|  | Location Description | N/A |
|  | Planned Activities | Carrying out CDBG activities |
| 2 | Project Name | Public Facilities Improvement - Children's Advocacy Center (CAC) Rehabilitation |
|  | Target Area |  |
|  | Goals Supported |  |
|  | Needs Addressed | Improving Public Facilities and Infrastructure Social Service Needs- Other |
|  | Funding | CDBG: $25,000.00 |
|  | Description | CAC facility improvements |
|  | Target Date | 9/30/2027 |
|  | Estimate the number and type of families that will benefit from the proposed activities | CAC helps hundreds of families each year. |
|  | Location Description | 640 Illinois Blvd, Hoffman Estates |
|  | Planned Activities | Continued facility improvements for the aging home that CAC operates within. |
| 3 | Project Name | Street & Related Improvements |
|  | Target Area |  |
|  | Goals Supported | Public Infrastructure Improvements |
|  | Needs Addressed | Improving Public Facilities and Infrastructure |
|  | Funding | CDBG: $183,662.00 |
|  | Description | Street, sidewalk and related work as determined by the Engineering team. |
|  | Target Date | 9/30/2027 |
|  | Estimate the number and type of families that will benefit from the proposed activities | 100 |
|  | Location Description | Address/location to be determined by Engineering team |
|  | Planned Activities | Street, sidewalk and related work as determined by the Engineering team. |
| 4 | Project Name | Clearbrook 1 - Bathroom |
|  | Target Area |  |
|  | Goals Supported | Public Facilities Improvements |
|  | Needs Addressed | Social Service Needs- Other |
|  | Funding | CDBG: $12,000.00 |
|  | Description | This project will support individuals with Intellectual and Developmental Disabilities (I/DD). The home will be more ADA compliant by removing a tripping/slipping hazard. A standing shower will provide more space for clients and the staff who assist with the bathing process, creating a more comfortable environment. As advocates for independence, this shower will allow some residents to have more self-autonomy. Many CILA clients will live at the same home for the remainder of their lives, or until they are moved to an intermediate care facility. Installing a shower will increase their quality of life. |
|  | Target Date | 9/30/2027 |
|  | Estimate the number and type of families that will benefit from the proposed activities | About 6-10 individuals |
|  | Location Description | 1174 Hunters Ridge E., Hoffman Estates, IL |
|  | Planned Activities | The home will be more ADA compliant by removing a tripping/slipping hazard for this bathroom project. A standing shower will provide more space for clients and the staff who assist with the bathing process, creating a more comfortable environment. As advocates for independence, this shower will allow some residents to have more self-autonomy. |
| 5 | Project Name | Clearbrook 2 - Shade |
|  | Target Area |  |
|  | Goals Supported | Public Facilities Improvements |
|  | Needs Addressed | Social Service Needs- Other |
|  | Funding | CDBG: $15,000.00 |
|  | Description | The Higgins Day Program will be installing retractable shade systems over the north side of the building. This will allow more opportunities for clients to utilize the facility. |
|  | Target Date | 9/30/2027 |
|  | Estimate the number and type of families that will benefit from the proposed activities | Various numbers of individuals with Intellectual and Developmental Disabilities (I/DD) will utilize the space on any given day - up to about 100 |
|  | Location Description | 1260 W. Higgins Road, Hoffman Estates, IL |
|  | Planned Activities | Installing retractable shade systems over the north side of the building. This will allow more opportunities for clients to utilize their facility. |
| 6 | Project Name | The SHARE Program Facility Improvements |
|  | Target Area |  |
|  | Goals Supported | Public Facilities Improvements |
|  | Needs Addressed | Improving Public Facilities and Infrastructure |
|  | Funding | CDBG: $100,000.00 |
|  | Description | Facility improvements at the SHARE Program by Leyden Family Services. |
|  | Target Date | 9/30/2027 |
|  | Estimate the number and type of families that will benefit from the proposed activities | The SHARE Program helps hundreds of families and this improvement will assist in doing that on an ongoing basis. |
|  | Location Description | 1776 Moonlake Blvd., Hoffman Estates, IL |
|  | Planned Activities | Facility improvements at the SHARE Program by Leyden Family Services. |

## AP-50 Geographic Distribution - 91.420, 91.220(f)

Description of the geographic areas of the entitlement (including areas of low-income and minority concentration) where assistance will be directed

Although the Village does not have any specific areas given limited funds, the Village will identify a street for reconstruction purposes as appropriate data is collected.

Geographic Distribution

| Target Area | Percentage of Funds |
| --- | --- |
| Village Wide | 100 |

Table 4 - Geographic Distribution

Rationale for the priorities for allocating investments geographically

No specific geographical investment area. The street rehabilitation project benefits residents in a CDBG-eligible low to moderate income neighborhood. The streets are chosen based off of condition, and then of the streets chosen by need, streets within eligible block groups are considered for CDBG funds.

Discussion

Infrastructure needs are located throughout the Village. While the centralized housing stock is older and often requires more SFR projects, lower-income homeowners exist throughout our boundaries.

The timing of the Village of Hoffman Estates’ street ratings and capital budget process, which is the system in which a street will be selected based upon need and eligibility, will not be formally determined until after the final annual action plan is submitted to HUD.
Additional information on HUD Low-Moderate Income Summary Data (LMSID) is located on this webpage: https://www.hudexchange.info/news/updates-to-low-moderate-income-summary-data-now-available/

## AP-75 Barriers to affordable housing -91.420, 91.220(j)

Introduction

The Village is fortunate to have a range of housing, including affordable housing options. The Village will continue to investigate policies that would address barriers to affordable housing.
The Village continues to take action to remove or modify public policies that serve as barriers to affordable housing such as land use controls, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment.
The Village intends on accommodating multi-family and mixed use development that is currently planned in two areas of town as well as continuing to make funds available for the Village’s owner-occupied, single family home rehabilitation program. The Village will also continue to ensure rental housing is maintained and renters’ rights protected through its residential rental license and inspection program. The Village has adopted the 2021 I-Codes through the International Code Council (ICC) and the 2020 National Electric Code (NEC), which are in place and enforced in order to protect the lives and safety of residents and visitors to the Village. This is a very standardized set of building codes across the nation.
The Village's fees - including building fees - are frequently reassessed and are currently lower than many comparable communities.
High sales and property taxes remain an issue in the State of Illinois, but this is beyond the jurisdiction or control of the Village. These taxes are regressive and have an outsized impact on low to moderate income level individuals and families who live in the Village.
The Village is heavily involved in regional public transportation and has worked extensively with the Regional Transportation Authority (RTA) to maintain a network of public buses, and even worked with the RTA to support and enhance their new Bus Mass Transit system that can take workers from their homes to jobs around the Chicagoland region. The Village also operates a subsidized taxi program for income-eligible residents.

Actions it planned to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment

Pertinent to the affordability of housing, the consultant team has identified areas where the Village can update and streamline its zoning for multifamily housing, including the creation of more predictable zoning entitlement processes, modernized multifamily zoning districts, and a Planned Development process that did not exist within the Village previously.
The new Code is intended to be a Unified Development Ordinance, drafted specifically to be user friendly, and readable to allow for easy access to potential developers.

Discussion

Our community is intertwined with adjacent suburbs and therefore our housing market can be challenging to define within our boundaries. This impacts efforts to manage affordability in housing. Hoffman Estates also offers a Single Family Home Repair Program to assist qualified homeowners offset some of the required costs that can be a major barrier to affordable housing. While CDBG funding is too low to make major impacts to our affordable housing, our development services team is working on ways to make the situation better for our pocket of the region.

## AP-85 Other Actions - 91.420, 91.220(k)

Introduction

This section discusses actions that the Village will take to address needs outside of those directly addressed through CDBG funds.

Actions planned to address obstacles to meeting underserved needs

While a lack of funding continues to be a challenge to address all of the needs identified in the Consolidated Plan, the Village will continue to partner and coordinate services wherever possible. To facilitate access to broadband/internet service for underserved residents, residents are referred to the appropriate one of the five library districts that cover the Village – all provide free internet access. Additionally, residents can be referred to low cost home internet access and/or computer hardware rebate programs represented in the following links:
https://www.fcc.gov/acp 
https://www.citizensutilityboard.org/wp-content/uploads/2020/01/LowIncomeInternet.pdf 
During the 2026 Program Year, continued consultation with stakeholders will remain important to ensuring the most important needs are identified and strategies for addressing them are developed and pursued.

Actions planned to foster and maintain affordable housing

The Village has identified an imbalance in the supply and demand for housing, and has actively taken steps to correct this. The Village commissioned a housing market study from Tracy Cross and Associates, which found that the Village could comfortably absorb 1,150 units per year over at least the next five years. Since receiving the results of that study, the Village has introduced a temporary Planned Development zoning entitlement process to allow for the consideration of new multifamily product as an interim step during the drafting of the new Unified Development Ordinance.
Based upon projects recently approved and under construction, development agreements in place, and projects that have received at least a courtesy review from the Village Board, the Village has approximately 2,700 new housing units in the pipeline. It is anticipated that these efforts to meet market demand will ease housing pressures in the Village, and therefore, pricing. The Village is also continuing to make funds available for the owner-occupied, single family home rehabilitation program. The Village will continue to ensure rental housing is maintained and renters’ rights protected through its residential rental license and inspection program.

Actions planned to reduce lead-based paint hazards

The Village plans on continuing coordination with the Cook County Department of Public Health to address lead-based paint hazards in the Village. As the State moves closer to decreasing the lead concentration threshold for children, the Village will continue to educate residents of potential hazards and provide lead hazard mitigation services wherever possible.
The Village of Hoffman Estates also offers a Single Family Home Repair Program which can help offset the costs associated with lead abatement’s need to follow numerous regulations for safety for projects within homes of homeowners who income qualify.

Actions planned to reduce the number of poverty-level families

The Village will continue to work with its business community and the State of Illinois to improve job training to close the gap between the jobs that are available in the community and the skillsets of residents. The Village has an active Economic Development Division with efforts that include attracting businesses that will offer employment for a variety of skill levels. Among actions during the 2026-2027 Program Year are continued collaboration with the Golden Corridor Advanced Manufacturing Partnership, provision and coordination of transit services, and the provision of health services through the Health and Human Services Department.

Actions planned to develop institutional structure

The Village will be continuing its effort to identify priority needs through an update to its Comprehensive Plan. Consideration of HUD priorities will be included in this update, particularly as they relate to housing. A strong and updated Comprehensive Plan will improve the Village’s ability to be responsive to needs through an improved institutional structure. Continued participation in the regional housing discussion through Cook County and the Continuum of Care will be important as well.

Actions planned to enhance coordination between public and private housing and social service agencies

During the 2026 Program Year, the Village will continue to address priority needs identified through consultation with housing associations. The owner-occupied single family home rehabilitation program will help reduce the cost burden for these individuals. Additionally, coordination of youth services, senior citizen services, and transit services will be a priority of Village Departments that provide them.

Discussion

Hoffman Estates will continue to work with area organizations to enable residents to use organizational services outside of those receiving CDBG funding to address ever-changing local needs.

# Program Specific Requirements

AP-90 Program Specific Requirements - 91.420, 91.220(l)(1,2,4)

Introduction

See table below.

Community Development Block Grant Program (CDBG)

Reference 24 CFR 91.220(l)(1)

Projects planned with all CDBG funds expected to be available during the year are identified in the Projects Table. The following identifies program income that is available for use that is included in projects to be carried out.

| 1. The total amount of program income that will have been received before the start of the next program year and that has not yet been reprogrammed | 23,010 |
| --- | --- |
| 2. The amount of proceeds from section 108 loan guarantees that will be used during the year to address the priority needs and specific objectives identified in the grantee's strategic plan. | 0 |
| 3. The amount of surplus funds from urban renewal settlements | 0 |
| 4. The amount of any grant funds returned to the line of credit for which the planned use has not been included in a prior statement or plan | 0 |
| 5. The amount of income from float-funded activities | 0 |
| Total Program Income: | 23,010 |

Other CDBG Requirements

| 1. The amount of urgent need activities | 0 |
| --- | --- |

| 2. The estimated percentage of CDBG funds that will be used for activities that benefit persons of low and moderate income.Overall Benefit - A consecutive period of one, two or three years may be used to determine that a minimum overall benefit of 70% of CDBG funds is used to benefit persons of low and moderate income. Specify the years covered that include this Annual Action Plan. | 100.00% |
| --- | --- |

Discussion

The Village plans to devote all activity funding to benefit low to moderate income persons. No urgent need activities are planned. Activities such as the Children's Advocacy Center & Clearbrook’s facility improvement projects may be presumed benefit as low to moderate income.